## About
ABOUT THIS GANTT CHART
Visualise and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Identifying Fraudulent Activity in Blockchain Transactions Using Machine Learning Algorithms
Teoh Kheng Hong |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project Start Date: | 2023-01-15 |  |  |  | September | [20 empty] | October
Scrolling Increment: | 240 | time axis 2023-09-12 to 2023-11-06
Milestone description | Category | Progress | Start | Days | time axis 2023-09-12 to 2023-11-06
Business Understanding
Understand Blockchain | Low Risk | 100% | 2023-01-13 | 3
Understand Blockchain (Purposes, structure, etc) | Low Risk | 100% | 2023-01-16 | 5
Usage of Blockchain in Industries | Low Risk | 100% | 2023-01-21 | 5
How Blockchain is ultilized in businesses | Low Risk | 100% | 2023-01-26 | 5
Financial institutes research studies | Med Risk | 100% | 2023-01-31 | 5
Project title, aims and objectives, scopes | Low Risk | 100% | 2023-02-05 | 2
Research Questions | Low Risk | 100% | 2023-02-07 | 1
Research Methodology | Low Risk | 100% | 2023-02-08 | 7
Literature Review | Med Risk | 100% | 2023-02-15 | 14
Presentation (RMCP) | Med Risk | 100% | 2023-03-01 | 1
Presentation (CP1) | Med Risk | 100% | TBA | 1
Finish Project Proposal | Milestone | 100% | 2023-03-10 | 0
Data Understanding
Identify, Select and Prepare Data Source | Low Risk | 100% | 2023-03-10 | 14
Describe data source | Low Risk | 100% | 2023-03-24 | 9
Verify Data Integrity | Med Risk | 100% | 2023-04-02 | 11
Initial Dataset analysis | Med Risk | 100% | 2023-04-13 | 7
Dataset Intitial Review | Med Risk | 100% | 2023-04-20 | 14
Ready Dataset for Next Process | Milestone | 100% | 2023-04-20 | 0
Data Preparation
Data Selection | Low Risk | 100% | 2023-05-04 | 14
Data Cleaning | Med Risk | 100% | 2023-05-18 | 28
Feature Engineering | High Risk | 100% | 2023-06-15 | 42
Data Integration | Low Risk | 100% | 2023-07-27 | 14
Data Formatting | Med Risk | 100% | 2023-08-10 | 42
Exploratory Data Analysis | Med Risk | 100% | 2023-09-21 | 14
Ready Dataset for ML | Milestone | 100% | 2023-10-05 | 0
Modeling
Selection | Low Risk | 100% | 2023-10-05 | 28
Training | Med Risk | 100% | 2023-11-02 | 14
Evaluation | Med Risk | 100% | 2023-11-16 | 14
Optimization | Med Risk | 100% | 2023-11-30 | 28
Model Ready | Milestone | 100% | 2023-12-28 | 0
Evaluation
Evaluate Results | Low Risk | 100% | 2023-12-28 | 14
Review Process | Low Risk | 100% | 2024-01-11 | 14
Results | Milestone | 0% | 2024-01-25 | 0
Deployment & Visualizations
Deployment | Med Risk | 100% | 2024-01-25 | 7
Model Comparisons | Med Risk | 100% | 2024-02-01 | 7
Release of Sample Model | Milestone | 100% | 2024-02-08 | 0
Documentation & Submission
Documentation | Med Risk | 100% | 2024-02-08 | 28
Presentation (CP2) | Med Risk | 100% | 2024-03-07 | 7
Submission | Milestone | 100% | 2024-05-13 | 0
TODAY()-Project_Start

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-12 |  |  |  |  | May | [20 empty] | June | [27 empty] | July
Scrolling Increment: | 1 | time axis 2024-05-13 to 2024-07-07
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-12 | 3 | M: 2; T: 2
Task 2 | Milestone |  |  | 2024-05-17 | 1 | bar: F
Task 3 | Low Risk |  | 50% | 2024-05-09 | 10
Task 4 | Milestone |  |  | 2024-06-01 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2024-05-18 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-05-18 | 13
Task 2 | On Track |  | 50% | 2024-05-20 | 9
Task 3 | Low Risk |  | 33% | 2024-05-25 | 11
Task 4 | Milestone |  |  | 2024-05-27 | 1 | bar: M
Task 5 |  |  |  | 2024-05-28 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-05-27 | 4
Task 2 | Med Risk |  |  | 2024-05-30 | 14
Task 3 | On Track |  |  | 2024-06-14 | 6
Task 4 | Goal |  |  | 2024-06-18 | 3 | T: 2; W: 2; T: 2
Task 5 | Low Risk |  |  | 2024-05-18 | 19
TITLE 4
Task 1 |  |  |  | 2024-06-21 | 15
Task 2 |  |  |  | 2024-07-05 | 5
Task 3 | Milestone |  |  | 2024-08-16 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Colour
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-12 |  |  |  |  | May | [20 empty] | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2024-05-17 to 2024-07-11
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-05-17 to 2024-07-11
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-12 | 3
Task 2 | Milestone |  |  | 2024-05-17 | 1 | bar: 2024-05-17
Task 3 | Low Risk |  | 50% | 2024-05-09 | 10
Task 4 | Milestone |  |  | 2024-06-01 | 1 | bar: 2024-06-01
Task 5 | Med Risk |  | 10% | 2024-05-18 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-05-18 | 13
Task 2 | On Track |  | 50% | 2024-05-20 | 9
Task 3 | Low Risk |  | 33% | 2024-05-25 | 11
Task 4 | Milestone |  |  | 2024-05-27 | 1 | bar: 2024-05-27
Task 5 |  |  |  | 2024-05-28 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-05-27 | 4
Task 2 | Med Risk |  |  | 2024-05-30 | 14
Task 3 | On Track |  |  | 2024-06-14 | 6
Task 4 | Goal |  |  | 2024-06-18 | 3 | 2024-06-18: 2; 2024-06-19: 2; 2024-06-20: 2
Task 5 | Low Risk |  |  | 2024-05-18 | 19
TITLE 4
Task 1 |  |  |  | 2024-06-21 | 15
Task 2 |  |  |  | 2024-07-05 | 5
Task 3 | Milestone |  |  | 2024-08-16 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one